## Project Plan (2)
PROJECT PLAN — MANAGEMENT & PERSONAL WORKSTREAMS
Pillar / Scope | Module / Section | Feature / Sub-Tab / Item | Frontend Effort (Days) | Backend Effort (Days) | Total Working Days
PART 1: MANAGEMENT WORKSTREAM & ALL FEATURES
Management | Dashboard | Admin Overview KPI Cards (Active Modules, Enrolled, Certifications, Completion Rate %) | 1.5 | 1 | 2.5
Management | Dashboard | Active Assignments Master Table (Search, Status Tabs, Department Filter) | 2 | 1 | 3
Management | Dashboard | Manager Team Dashboard (Direct Reports Roster, Team Completion %, Overdue Alerts) | 2 | 1.5 | 3.5
Management | Dashboard | One-Click 'Nudge / Remind' Action Button for Overdue Direct Reports | 1 | 0.5 | 1.5
Management | Course Catalogue | Upload Courses (SCORM 1.2 / 2004 ZIP Dropzone, Video, PDF, Manifest Auto-Inspector) | 2.5 | 2.5 | 5
Management | Course Catalogue | Course Management (One-Click Publish Toggle, Edit Metadata, Delete with File Cleanup) | 1.5 | 1 | 2.5
Management | Course Catalogue | Course Details & Syllabus Slide-Over Drawer (Admin View) | 1.5 | 0.5 | 2
Management | Course Catalogue | Course Enrolled Learners Roster Drawer (Filter by Status, Scores) | 1.5 | 1 | 2.5
Management | Course Assignment | Assign Course Modal (Individual, Department, Designation) | 2 | 1.5 | 3.5
Management | Course Assignment | Searchable Employee Multi-Select Picker (Live from Employee Central) | 1.5 | 1 | 2.5
Management | Course Assignment | Preset Due Dates Configuration (7d, 14d, 30d, Custom Date Picker) | 1 | 0.5 | 1.5
Management | Course Assignment | Mandatory Compliance vs Elective Flag & Notification Dispatch | 1 | 0.5 | 1.5
Management | Users Management | Existing one from Employee Central (Live sync with employees, departments, designations) | 1 | 1.5 | 2.5
Management | Users Management | Add External Employee (Modal: Name, Email, Phone, Vendor/Company, Contractor ID, Validity) | 2 | 1.5 | 3.5
Management | Users Management | Add External Candidate (Pre-boarding / Candidate Training link from Source/ATS) | 1.5 | 1.5 | 3
Management | Users Management | External User Invite & One-Click Magic Link Credential Dispatch | 1 | 1.5 | 2.5
Management | Users Management | Audience Segmentation & Batch Assignments (Internal Departments vs External Cohorts) | 1.5 | 1 | 2.5
Management | Employee Central Sync | New Hire Onboarding Auto-Assignment Rule (Automatic enrollment on employee creation) | 0.5 | 1.5 | 2
Management | Employee Central Sync | Skill Matrix Auto-Update on Course Completion (Levels up skill in HR profile) | 1 | 1.5 | 2.5
Management | Employee Central Sync | Exit Clearance Compliance Verification (Checks mandatory training before relieving) | 0.5 | 1 | 1.5
Management | Assessments & Certificates | Attach Assessment to Course Module (Verify Hub Question Bank Link) | 1 | 1.5 | 2.5
Management | Assessments & Certificates | Passing Score % & Max Retake Attempts Configuration | 0.5 | 0.5 | 1
Management | Assessments & Certificates | Automated PDF Certificate Generator Engine (Serial ID, QR Code Generation) | 1 | 2 | 3
Management | Assessments & Certificates | Public Certificate Verification Page Setup (/verify-certificate/:certId) | 1.5 | 1 | 2.5
Management | Reports & Export | Report Configurator (Course Completion, Department Compliance, Overdue Roster) | 1.5 | 1 | 2.5
Management | Reports & Export | One-Click Export to Excel (.xlsx) and CSV for Statutory Compliance Audits | 1.5 | 1.5 | 3
PART 2: PERSONAL WORKSTREAM & ALL FEATURES
Personal | Personal Dashboard | Learner Dashboard Summary Cards (Enrolled, In Progress, Completed, Average Score) | 1.5 | 0.5 | 2
Personal | Personal Dashboard | 'Continue Learning' Smart Action Card (Instant resume from exact saved bookmark) | 1.5 | 0.5 | 2
Personal | Personal Dashboard | Learning Streak Flame Counter & Daily Milestone Tracker | 1 | 0.5 | 1.5
Personal | Personal Dashboard | Active Tasks Roster & Due Date Countdown Pills ('Due in 2 days', 'Overdue') | 1.5 | 0.5 | 2
Personal | Personal Catalogue | Browse Course Catalogue Grid (Live Search, Format Tabs, Department & Tag Filters) | 2 | 1 | 3
Personal | Personal Catalogue | Course Preview & Syllabus Details Slide-Over Drawer | 1.5 | 0.5 | 2
Personal | Personal Catalogue | Self-Enroll in Elective Courses Action Button | 1 | 0.5 | 1.5
Personal | Course Player | Universal SCORM 1.2 & 2004 Runtime Player (Dual window.API Bridge, CMI Auto-Sync) | 2 | 1.5 | 3.5
Personal | Course Player | Native Video Player (Speed 0.75x–2x, Resume Timestamp) & In-Browser PDF Reader | 1.5 | 0.5 | 2
Personal | Course Player | Player Top Bar (Course Breadcrumbs, Status Pill, Fullscreen Toggle, Exit Safeguard) | 1 | 0.5 | 1.5
Personal | Course Player | Collapsible Outline Sidebar & Completion Celebration Trigger | 1.5 | 0.5 | 2
Personal | Personal Profile Tabs | Employee Profile — 'Training & Learning' Dedicated Tab (/deploy/employees/:code) | 1.5 | 1 | 2.5
Personal | Personal Profile Tabs | Active & Overdue Training Table with Live Progress % & Deadlines | 1 | 0.5 | 1.5
Personal | Personal Profile Tabs | Completed Training History Ledger with Final Scores & Certificate Links | 1 | 0.5 | 1.5
Personal | Personal Profile Tabs | Direct '+ Assign Training' Action Button from Employee Profile | 1 | 0.5 | 1.5
Personal | Personal Assessments | Timed Quiz Taking Interface (Countdown Clock, MCQ, Multi-Select, Auto-Submit) | 2 | 1 | 3
Personal | Personal Assessments | Diagnostic Scorecard Modal (Pass/Fail Banner, Review Answers, Retake Action) | 1.5 | 1 | 2.5
Personal | Personal Certificates | In-Browser Certificate Viewer Modal Preview | 1 | 0.5 | 1.5
Personal | Personal Certificates | Download High-Resolution PDF Certificate & Print Buttons | 1 | 0.5 | 1.5
Personal | Personal Certificates | Add to LinkedIn Profile 1-Click Share Button | 1 | 0.5 | 1.5
Personal | External Employee View | Dedicated External Learner Shell (Branded view hiding internal HRMS tabs) | 1.5 | 0.5 | 2
Personal | External Employee View | Curated External Course Catalogue (Only authorized vendor/contractor courses) | 1.5 | 1 | 2.5
Personal | External Employee View | Contractor 'My Learning' Portal (Assignments, Progress Bars, Due Dates) | 1.5 | 0.5 | 2
Personal | External Employee View | External Player & Assessment Execution (Verified progress commit & scoring) | 1 | 0.5 | 1.5
Personal | External Employee View | External Certificate View & PDF Download (With partner company attribution) | 1 | 0.5 | 1.5
Personal | External Candidate View | Candidate Pre-Boarding Portal Shell (Source module link before Day 1) | 1.5 | 0.5 | 2
Personal | External Candidate View | Assigned Pre-Joining Modules (Company Intro, Policy, Welcome Pack, Tech Prep) | 1 | 1 | 2
Personal | External Candidate View | Candidate Completion Status Sync (Alerts HR recruiter when pre-boarding is done) | 0.5 | 1 | 1.5
— | TOTAL WORKING DAYS | Complete End-to-End Scope (Management + Personal) | 71.5 | 49.5 | 121

## Features
LEARNING CENTRAL (FORGE) — PRACTICAL UI/UX & EMPLOYEE CENTRAL FEATURE MATRIX
Actionable, screen-by-screen feature blueprint focusing on user flows, buttons, filters, catalog UI, and deep Employee Central (HRMS) integration.
# | Page / Screen | UI Section / Component | Feature Name | Buttons, Filters & Controls | Functional Flow & Logic | Employee Central & Platform Integration | Priority | Status
1 | Course Catalogue | Top Filter & Search Bar | Instant Live Search Input | Search text input with clear 'X' button and magnifying glass icon | As user types, course cards filter in real-time matching course title, description, or tags without full page reload. | Matches course tags tied to Employee Central skill taxonomy. | P1 | Completed
2 | Course Catalogue | Top Filter & Search Bar | Course Format Filter Tabs | Pill buttons: 'All Formats', 'SCORM Package', 'Video', 'Document/PDF', 'External Link' | Clicking a format tab instantly filters the catalog grid to show only matching delivery types. | Allows employees to find quick micro-videos vs formal SCORM training. | P1 | Completed
3 | Course Catalogue | Top Filter & Search Bar | Department Filter Dropdown | Dropdown select populated dynamically with company departments (Tech, HR, Sales, Ops, Finance) | Selecting a department shows courses tagged for or recommended to that specific business unit. | Directly queries Employee Central 'departments' list from HRMS database. | P1 | In Progress
4 | Course Catalogue | Top Filter & Search Bar | Difficulty Level Filter | Dropdown select: 'All Levels', 'Beginner', 'Intermediate', 'Advanced' | Filters the catalog grid by course difficulty level badge. | Helps employees filter upskilling courses matching their current role tenure. | P2 | Completed
5 | Course Catalogue | Top Filter & Search Bar | Estimated Duration Filter | Dropdown / pill filter: '< 15 mins', '15-30 mins', '30-60 mins', '1+ hours' | Filters courses by estimated completion time stored in duration_minutes. | Enables quick micro-learning searches during work breaks. | P2 | Completed
6 | Course Catalogue | Top Filter & Search Bar | Category & Skill Tag Chips | Horizontal scrollable row of tag chips (e.g. 'Cybersecurity', 'POSH', 'React', 'Leadership') | Clicking tag chip toggles multi-select filter; active tags highlight with purple pill styling. | Tags map directly to Employee Central skills matrix. | P2 | Completed
7 | Course Catalogue | Top Filter & Search Bar | Publish Status Filter (Admin View) | Segmented toggle buttons: 'All', 'Published', 'Draft / Unpublished' | Visible only to L&D Admins and HR Managers; lets administrators audit unpublished or draft courses. | Restricted via forge.courses.manage permission gate. | P1 | Completed
8 | Course Catalogue | Catalog View Controls | Grid vs List Layout Switcher | Two toggle icons: 3x3 Grid Icon and List View Icon | Switches catalog layout between visual card grid and a compact table view with sorting. | Remembers user view preference in browser localStorage. | P2 | Planned
9 | Course Catalogue | Course Card Component | Course Thumbnail & Format Badge | Visual image container with fallback branded gradient + top-left Format Badge ('SCORM', 'VIDEO', 'DOC') | Renders course thumbnail preview; shows clear visual badge of course delivery medium. | Supports company brand asset library thumbnails. | P1 | Completed
10 | Course Catalogue | Course Card Component | SCORM Edition Badge | Purple pill badge: 'SCORM 1.2' or 'SCORM 2004' | Displays automatically when course type is SCORM, indicating verified engine compatibility. | Parsed automatically by ScormService during ZIP upload. | P1 | Completed
11 | Course Catalogue | Course Card Component | Mandatory vs Elective Pill | Red outline pill: 'Mandatory Compliance' / Blue outline pill: 'Elective Upskilling' | Immediately alerts learners if course is a compulsory company-wide requirement. | Tied to Employee Central compliance tracking rules. | P1 | In Progress
12 | Course Catalogue | Course Card Component | Course Metadata Info Bar | Clock icon with duration (e.g. '45m'), user icon with enrolled count (e.g. '128 enrolled') | Shows quick glanceable metrics before user clicks to explore details. | Live count of total enrollments in the tenant schema. | P1 | Completed
13 | Course Catalogue | Course Card Component | Action Button: 'Start / Continue Learning' | Primary action button on card: changes to 'Continue' with progress % if already enrolled, or 'Start' if assigned | Clicking launches player (/forge/play/:id) directly at the user's saved location. | Checks forge_enrollments table for logged-in employee code. | P1 | Completed
14 | Course Catalogue | Course Card Component | Action Button: 'Self-Enroll' | Secondary button on elective courses: 'Enroll in Course' | Creates enrollment record with status='assigned' and immediately refreshes card state. | Records employee_code and logs enrollment in Employee Central learning record. | P1 | In Progress
15 | Course Catalogue | Course Card Component | Admin Quick Action Menu | Three-dots dropdown menu: 'Edit Metadata', 'Assign to Team', 'Toggle Publish', 'Delete Course' | Allows L&D admins to manage courses directly from the catalog view without digging through settings. | Protected by forge.courses.manage permission. | P1 | Completed
16 | Course Catalogue | Course Detail Drawer | Slide-Over Course Details Drawer | Slide-over right drawer showing full syllabus, learning objectives, prerequisites, and target skills | Opens when clicking course title or card body; lets learner preview curriculum before starting. | Displays target skills that will be credited to employee's profile upon completion. | P2 | In Progress
17 | Course Catalogue | Header Action Bar | Primary Action Button: 'New Course / Upload' | Prominent purple button with '+' icon: 'New Course' | Opens the CourseUploadModal for SCORM ZIP upload or URL creation. Visible to Admins/Trainers. | Restricted to L&D Admin and HR Manager roles. | P1 | Completed
18 | Course Catalogue | Catalog Empty State | Empty State Illustration & Clear Filters Button | Clean graphic with 'No courses found' heading and 'Reset All Filters' button | Provides clear fallback when search query or filter combination returns zero results. | Guides user back to default catalog view with one click. | P2 | Completed
19 | My Learning Portal | Header Metric Cards | Learner KPI Summary Banner | 4 stat cards: 'Courses Enrolled', 'In Progress', 'Completed', 'Average Score %' | Gives employee an immediate snapshot of their personal learning velocity and compliance status. | Calculated live from forge_enrollments for the authenticated employee. | P1 | Completed
20 | My Learning Portal | Filter Tabs | Status Navigation Tabs | Tab bar with badge counters: 'All (6)', 'In Progress (2)', 'Completed (3)', 'Overdue (1)' | Clicking tabs filters the enrolled courses list; counters update in real-time. | Overdue tab highlights urgent compliance tasks requiring immediate action. | P1 | Completed
21 | My Learning Portal | Search & Sort Bar | Search My Courses & Sort Selector | Search input + Sort dropdown ('Due Date: Soonest', 'Recently Accessed', 'Progress: High to Low') | Allows learners with multiple assignments to quickly locate a specific course. | Helps prioritize urgent mandatory courses approaching deadline. | P2 | Completed
22 | My Learning Portal | Enrolled Course Card | Visual Progress Bar & Percentage | Horizontal purple progress bar + percentage text (e.g. '68% Completed') | Displays real-time progress through SCORM package or video chapters. | Updated automatically on every SCORM commit event. | P1 | Completed
23 | My Learning Portal | Enrolled Course Card | Dynamic Status Badge | Color-coded pill: Yellow 'Assigned', Blue 'In Progress', Green 'Completed', Red 'Overdue' | Clear visual indicator of current lifecycle status for each assigned course. | Status auto-transitions based on started_at, completed_at, and due_date. | P1 | Completed
24 | My Learning Portal | Enrolled Course Card | Due Date Pill with Smart Countdown | Calendar icon with badge: 'Due in 3 days' (amber), 'Overdue by 2 days' (red), 'No Deadline' (gray) | Calculates relative days remaining until due date, turning red when overdue. | Synced with assignment due_date set by manager or onboarding workflow. | P1 | Completed
25 | My Learning Portal | Enrolled Course Card | Score & Grade Display Badge | Trophy icon with score badge (e.g. 'Score: 92% — Passed') | Renders final assessment score recorded from SCORM CMI data or Verify quiz engine. | Only appears once course has an evaluated score. | P1 | Completed
26 | My Learning Portal | Enrolled Course Card | Smart Action Button: 'Start Course' | Primary action button: 'Start Course' with play icon | Displayed when enrollment status is 'assigned' (0% progress); launches player at module 1. | Sets started_at timestamp and transitions status to 'in_progress'. | P1 | Completed
27 | My Learning Portal | Enrolled Course Card | Smart Action Button: 'Continue Learning' | Primary action button: 'Continue Learning' with arrow icon | Displayed when course is 'in_progress'; launches player and restores exact SCORM suspend location. | Pulls suspend_data and cmi.core.lesson_location from database. | P1 | Completed
28 | My Learning Portal | Enrolled Course Card | Action Button: 'Download Certificate' | Green outline button: 'Download Certificate' with certificate icon | Appears only on completed courses; opens/downloads verified PDF certificate. | Validates that status is 'completed' before enabling download. | P1 | In Progress
29 | My Learning Portal | Enrolled Course Card | Secondary Action: 'Review Material' | Secondary button: 'Review Course' with eye icon | Allows learner to revisit completed courses without overwriting their passed score. | Launches player in review mode. | P2 | Completed
30 | My Learning Portal | Empty State | Empty Learning State & Explore CTA | Friendly graphic: 'You have no courses in progress' + 'Explore Course Catalogue' button | Guides learners to the catalog tab when they have zero active courses. | Switches Forge active tab to 'courses' on click. | P1 | Completed
31 | Course Player | Top Navigation Bar | Exit & Back Navigation Button | Left chevron button: 'Back to Learning Central' | Prompts SCORM LMSCommit to ensure latest progress is saved, then navigates back to /forge. | Guarantees no progress data loss on sudden browser exit. | P1 | Completed
32 | Course Player | Top Navigation Bar | Course & Module Title Breadcrumbs | Header text displaying 'Course Title > Current Chapter Title' | Keeps learner oriented inside multi-chapter or multi-SCO packages. | Updates dynamically as learner advances through modules. | P1 | Completed
33 | Course Player | Top Navigation Bar | Live Progress & Status Pill | Badge showing 'Status: In Progress' and live score counter if evaluated | Gives continuous feedback on whether the module has met completion requirements. | Listens to SCORM API bridge state updates in real time. | P1 | Completed
34 | Course Player | Top Navigation Bar | Fullscreen Mode Toggle Button | Maximize/Minimize icon button: 'Toggle Fullscreen' | Expands player to true distraction-free fullscreen using browser Fullscreen API. | Maximizes screen real estate for complex interactive simulations. | P2 | Completed
35 | Course Player | Player Core Container | Universal SCORM 1.2 Runtime Container | Seamless iframe container with injected window.API bridge | Handles LMSInitialize, LMSGetValue, LMSSetValue, LMSCommit, and LMSFinish with zero cross-origin errors. | Auto-syncs CMI data to /api/forge/progress/scorm-commit endpoint. | P1 | Completed
36 | Course Player | Player Core Container | Universal SCORM 2004 Runtime Container | Seamless iframe container with injected window.API_1484_11 bridge | Handles SCORM 2004 Initialize, GetValue, SetValue, Commit, Terminate, tracking completion_status & success_status. | Auto-maps passed/completed status to forge_enrollments table. | P1 | Completed
37 | Course Player | Player Core Container | Native Video Player Controls | Play/Pause, scrub timeline, playback speed (0.75x-2x), volume slider, time counter | Built-in HTML5 player for MP4 video courses with bookmarking of last played second. | Stores playback timestamp in cmi_data for resume playback. | P1 | In Progress
38 | Course Player | Player Core Container | PDF Document Reader Controls | Page navigation arrows, zoom in/out buttons, page jump input, download toggle | Zero-footprint in-browser reader for SOP documents, employee handbooks, and policy slides. | Tracks page scrolling to verify full document review. | P1 | In Progress
39 | Course Player | Sidebar Drawer | Collapsible Course Outline / Table of Contents | Slide-out drawer button on right side: lists all chapters/modules with checkmarks | Learners can jump between unlocked chapters; completed chapters show green checkmark icon. | Enforces sequential locking if prerequisite gating is enabled. | P2 | In Progress
40 | Course Player | Player Footer Bar | Previous & Next Module Navigation | Bottom action buttons: '< Previous Module' and 'Next Module >' | Allows learner to advance through multi-module curriculums sequentially. | Next button enables automatically once current module reports completion. | P1 | In Progress
41 | Course Player | Notification System | Completion Celebration Toast & Banner | Celebratory modal/toast: 'Congratulations! Module Completed — Score: 95%' | Triggers immediately when SCORM package reports 'completed' or 'passed'. | Congratulates employee and provides button to return to dashboard. | P1 | Completed
42 | Course Player | Exit Protection | Unsaved Progress Exit Warning Modal | Confirmation dialog: 'Are you sure you want to exit? Your progress is being saved...' | Safeguards against accidental tab closing before the final SCORM Commit network call completes. | Ensures 100% data integrity for compliance audit records. | P1 | Completed
43 | Course Management Studio | Course Management Table | Course Inventory Data Table | Table listing all courses with Title, Type, Duration, Enrollments Count, Published Toggle, Actions | Central admin dashboard for reviewing, filtering, and managing all learning assets. | Shows total number of enrolled employees from Employee Central. | P1 | Completed
44 | Course Management Studio | Action Header | Button: 'New Course / Upload' | Primary action button: 'New Course' with upload icon | Opens the CourseUploadModal for SCORM ZIP upload or manual course authoring. | Gated by forge.courses.manage permission. | P1 | Completed
45 | Course Management Studio | Course Upload Modal | Course Format Selector Tabs | Radio cards / tabs: 'SCORM Package (.zip)', 'Video (MP4 / Stream)', 'Document (PDF)', 'External URL' | Switching tab dynamically adjusts the modal inputs to match the chosen format. | Ensures clean metadata collection tailored to each content type. | P1 | Completed
46 | Course Management Studio | Course Upload Modal | SCORM Drag-and-Drop Dropzone | Dashed border dropzone accepting .zip archives with file picker browse button | User drags any SCORM zip; displays file name and size with clear visual feedback. | Validates file extension before uploading to backend. | P1 | Completed
47 | Course Management Studio | Course Upload Modal | Live Upload Progress Bar | Animated progress bar showing upload % and transfer speed | Provides real-time feedback during large SCORM package uploads (up to 200MB). | Prevents user from clicking submit multiple times. | P1 | Completed
48 | Course Management Studio | Course Upload Modal | Auto-Inspected Manifest Preview Card | Card previewing parsed Title, Detected SCORM Version ('1.2' / '2004'), and Launch File ('index.html') | Automatically populated immediately after ZIP upload by backend ScormService. | Verifies manifest validity before course is saved to the database. | P1 | Completed
49 | Course Management Studio | Course Upload Modal | Course Metadata Form Fields | Inputs: Title, Description (textarea), Estimated Duration (minutes), Difficulty dropdown | Allows admin to override or enrich the automatically extracted manifest metadata. | Saves directly to forge_courses table. | P1 | Completed
50 | Course Management Studio | Course Upload Modal | Target Department & Designation Multi-Select | Searchable multi-select dropdowns populated with Employee Central departments and job titles | Tags course for specific departments (e.g. Sales, Engineering) for catalog filtering. | Directly queries Employee Central master lists. | P1 | In Progress
51 | Course Management Studio | Course Upload Modal | Target Skill Tags Input | Chip input: type skill name and hit Enter (e.g. 'Customer Service', 'Python', 'ISO-27001') | Maps course completion to specific skill tags that sync to employee profiles. | Connects Forge courses directly to Employee Central skills matrix. | P1 | Completed
52 | Course Management Studio | Course Upload Modal | Thumbnail Image Dropzone / URL | Image dropzone for course cover banner (PNG/JPG) or custom URL input | Provides visual branding for the course card in the catalog and learner portal. | Auto-generates high-res and mobile-optimized thumbnails. | P2 | Completed
53 | Course Management Studio | Course Upload Modal | Toggle: 'Publish Immediately' | Switch toggle: 'Publish Immediately' (active = visible in catalog, inactive = saved as draft) | Lets admins stage courses as drafts for review before making them visible to employees. | Sets is_published boolean in forge_courses table. | P1 | Completed
54 | Course Management Studio | Course Upload Modal | Action Buttons: 'Save Course' & 'Cancel' | Secondary 'Cancel' button and primary 'Create Course' button with spinner state | Submits multipart form to /api/forge/courses/upload-scorm and refreshes catalog table on success. | Triggers success toast notification upon successful creation. | P1 | Completed
55 | Course Management Studio | Table Actions | One-Click Publish / Unpublish Switch | Toggle switch right on the course table row: toggles green (Published) vs gray (Draft) | Instantly publishes or unpublishes course from catalog without opening edit modal. | Calls POST /api/forge/courses/{id}/publish in background. | P1 | Completed
56 | Course Management Studio | Table Actions | Action Button: 'Assign Training' | Button with user-plus icon: 'Assign' on each course row | Opens the AssignCourseModal pre-populated with this specific course ID. | Fast track for L&D admins to dispatch training assignments. | P1 | Completed
57 | Course Management Studio | Table Actions | Action Button: 'Edit Course' | Pencil icon button: opens edit modal to update title, description, duration, or tags | Allows editing metadata or replacing media file without breaking existing enrollment history. | Calls PUT /api/forge/courses/{id}. | P1 | Completed
58 | Course Management Studio | Table Actions | Action Button: 'Delete Course' | Trash icon button: opens confirmation dialog ('Are you sure you want to delete this course?') | Deletes course record from database and securely removes extracted files from disk. | Calls ScormService.delete_course_files(course_id). | P1 | Completed
59 | Course Management Studio | Table Actions | Action Button: 'View Enrolled Roster' | Users icon button: opens slide-over drawer showing all employees currently assigned to this course | Displays list of enrolled employees with their status, scores, and completion timestamps. | Queries forge_enrollments joined with employees table. | P1 | Completed
60 | Assign Training Modal | Course Selection | Course Selector Dropdown | Dropdown with course thumbnail, title, and SCORM badge; auto-locked if launched from course card | Allows admin to pick which course to assign, or pre-selects course if triggered from catalog. | Lists all published active courses. | P1 | Completed
61 | Assign Training Modal | Target Segment Selector | Assignment Target Segment Radio Tabs | Segment tabs: 'Select Individual Employees', 'By Department', 'By Designation / Role', 'All Employees' | Allows assigning to individual staff or broadcasting to entire departments in one click. | Streamlines company-wide compliance rollout (e.g. POSH training for everyone). | P1 | In Progress
62 | Assign Training Modal | Target Segment: Department | Department Multi-Select Dropdown | Searchable multi-select dropdown: 'Select Departments' (e.g. 'Engineering', 'Customer Support') | Selecting a department automatically queues all active employees belonging to that department. | Queries active employees from Employee Central where department = selected. | P1 | In Progress
63 | Assign Training Modal | Target Segment: Designation | Designation Multi-Select Dropdown | Searchable multi-select dropdown: 'Select Designations' (e.g. 'Team Lead', 'Senior Developer') | Enables role-specific training (e.g. 'Managerial Effectiveness' assigned to all Team Leads). | Queries Employee Central employees where designation = selected. | P1 | In Progress
64 | Assign Training Modal | Target Segment: Individual | Searchable Employee Multi-Select Picker | Live search input matching employee name, employee code, or email with checkbox results list | Admin can type 'John' or 'EMP-104' to quickly find and checkmark specific team members. | Fetches live list of active employees from /api/employees endpoint. | P1 | Completed
65 | Assign Training Modal | Employee Selection Roster | Selected Employees Tag Chips Roster | Roster of selected employee chips with small avatar, name, and 'X' remove button + counter pill | Gives immediate visual confirmation of who will receive the training assignment. | Shows counter: '18 employees selected'. | P1 | Completed
66 | Assign Training Modal | Bulk Action Controls | Quick Action: 'Select All Active Employees' | Checkbox / button: 'Select All Filtered Employees' | Allows one-click selection of 500+ employees matching current search or department filter. | Saves immense manual clicking during enterprise-wide training assignments. | P1 | Completed
67 | Assign Training Modal | Deadline Configuration | Due Date Picker with Quick Preset Buttons | Calendar date input + 4 preset buttons: '7 Days', '14 Days', '30 Days', 'No Deadline' | Clicking preset button auto-calculates target completion date; stores in due_date timestamp. | Used by notification engine to trigger automated overdue warnings. | P1 | Completed
68 | Assign Training Modal | Assignment Nature | Mandatory Compliance vs Elective Toggle | Toggle switch: 'Mark as Mandatory Compliance Training' | Flags the assignment so it displays with high-priority red styling on employee dashboard. | Enforces manager escalation workflows for non-completion. | P1 | In Progress
69 | Assign Training Modal | Notification Trigger | Checkbox: 'Send Email & In-App Notification' | Checkbox (checked by default): 'Notify assigned employees via email and dashboard alert' | When checked, dispatches instant welcome email with course link to all assigned employees. | Integrates with Phygitron email dispatch service. | P1 | In Progress
70 | Assign Training Modal | Action Buttons | Action Buttons: 'Cancel' & 'Assign Training' | Secondary 'Cancel' button and primary 'Assign Training' button with loading spinner | Batch inserts records into forge_enrollments and initializes forge_progress; shows success toast. | Handles conflict upsert safely if employee was previously assigned. | P1 | Completed
71 | Employee Central Integration | Employee Profile Page | Dedicated 'Training & Learning' Profile Tab | Tab button on Employee Profile (/deploy/employees/:code) alongside 'Personal', 'Attendance', 'Assets' | Displays employee's complete corporate learning journey directly inside their HRMS profile. | Accessible to HR admins, managers, and the employee themselves. | P1 | In Progress
72 | Employee Central Integration | Employee Profile Tab | Active Courses & Overdue Assignments Table | Table listing assigned courses, progress %, assigned date, due date, and overdue flag | HR and managers can see at a glance whether the employee is compliant with required training. | Queries forge_enrollments where employee_code = employee.employee_code. | P1 | In Progress
73 | Employee Central Integration | Employee Profile Tab | Completed Training History & Certifications Ledger | Table of completed courses, completion dates, test scores, and 'View Certificate' link | Serves as the employee's official statutory training transcript inside the HRMS. | Permanent record that remains intact across employee tenure. | P1 | In Progress
74 | Employee Central Integration | Employee Profile Tab | Quick Action Button: 'Assign Training' | Button: '+ Assign Course' located on employee profile training tab | Opens AssignCourseModal pre-populated with this specific employee code. | Allows HR or manager to assign targeted training directly from the employee profile. | P1 | In Progress
75 | Employee Central Integration | Onboarding Automation | New Hire Onboarding Auto-Assignment Trigger | Background automation rule triggered when a new employee is created in Employee Central | Automatically enrolls the new hire into standard onboarding courses (e.g. POSH, Information Security, Company Culture). | Hooks into EmployeeService.create_employee() lifecycle hook. | P1 | In Progress
76 | Employee Central Integration | Role Change Automation | Department / Role Transfer Course Reassignment | Automated check when an employee's department or designation is updated in Employee Central | Prompts manager to assign role-specific training modules required for the new position. | Keeps workforce qualifications aligned with organizational movements. | P2 | Planned
77 | Employee Central Integration | Skills Matrix Sync | Skill Matrix Proficiency Auto-Update | Backend sync: passing an accredited course updates employee's verified skill level in HRMS | When an employee passes a course tagged with 'Customer Service', their profile skill matrix gains a verified badge. | Eliminates manual skill updating by managers. | P2 | In Progress
78 | Employee Central Integration | Performance Review Sync | Performance Review Training Hours & Score Sync | Widget in Employee Central Performance Review tab showing training hours completed in review period | Allows managers during annual appraisals to evaluate employee's continuous learning dedication. | Pulls aggregated training hours and average scores from Forge database. | P2 | Planned
79 | Employee Central Integration | Offboarding Checklist | Exit Clearance Compliance Verification | Checklist item in Employee Central Exit/Resignation workflow: 'Mandatory Training Cleared' | Verifies employee has completed all legally required compliance courses before generating relieving letter. | Ensures company audit compliance defense before employee leaves. | P2 | Planned
80 | Employee Central Integration | Document Repository | Earned Certificate Sync to Employee Document Locker | Automated copy of earned certificate PDF saved to employee's document vault in Employee Central | HR can view and print employee certificates alongside their ID proofs and contracts. | Saves into /data/documents/employees/{code}/certificates/. | P2 | In Progress
81 | Manager Team Dashboard | Team Header & Scope | Direct Reports Filter & Team Header | Header showing 'My Team (8 members)' with team completion rate % ring | Filters view strictly to direct reports where reporting_manager_id matches logged-in user. | Directly integrates with Employee Central manager hierarchy. | P1 | In Progress
82 | Manager Team Dashboard | Team Summary Metrics | Team Compliance Overview Cards | 3 metric cards: 'Assigned to Team', 'Team Completed', 'Team Overdue Tasks' | Gives managers immediate visibility into team-wide compliance risks. | Highlights overdue tasks in urgent amber/red styling. | P1 | In Progress
83 | Manager Team Dashboard | Team Roster Table | Direct Reports Progress Roster | Table listing Employee Name, Code, Role, Active Courses Count, Overall Progress %, Overdue Count, Actions | Central command center for supervisors to monitor learning progress across their team. | Columns support sorting by overdue count and progress %. | P1 | In Progress
84 | Manager Team Dashboard | Table Action Button | One-Click 'Nudge / Remind' Action Button | Bell icon button: 'Nudge' next to employees with overdue or pending courses | Sends instant email and dashboard alert reminding the employee of their deadline. | Logs reminder timestamp to prevent spamming more than once per 24 hours. | P1 | In Progress
85 | Manager Team Dashboard | Table Action Button | Slide-Over: 'View Employee Learning Details' | Button: 'View Details' opening right drawer with detailed breakdown of all courses assigned to this employee | Manager can see module-level scores, last access dates, and time spent. | Helps managers conduct 1-on-1 development conversations. | P2 | In Progress
86 | Manager Team Dashboard | Header Action Button | Action Button: 'Assign Training to Team' | Primary button: '+ Assign Course to My Team' | Opens AssignCourseModal with all direct reports pre-checked in the recipient roster. | Allows a manager to quickly roll out a new skill course to their entire team in 10 seconds. | P1 | In Progress
87 | Manager Team Dashboard | Export Action | Button: 'Export Team Compliance Report' | Download button: exports current team training roster and status to CSV/Excel | Manager can present team compliance data to department heads or auditors. | Generates clean branded spreadsheet. | P2 | In Progress
88 | Forge Dashboard Overview | Top KPI Metric Cards | Stat Card: Active Published Courses | Stat card with BookOpen icon showing total published courses available | Queries forge_courses where is_published = true. | Live metric from /api/forge/stats. | P1 | Completed
89 | Forge Dashboard Overview | Top KPI Metric Cards | Stat Card: Enrolled Employees (Unique Learners) | Stat card with Users icon showing count of distinct employees enrolled in training | Queries count of distinct employee_code in forge_enrollments. | Live metric from /api/forge/stats. | P1 | Completed
90 | Forge Dashboard Overview | Top KPI Metric Cards | Stat Card: Certifications Issued | Stat card with Award icon showing total completed course milestones | Queries count of forge_enrollments where status = 'completed'. | Live metric from /api/forge/stats. | P1 | Completed
91 | Forge Dashboard Overview | Top KPI Metric Cards | Stat Card: Overall Completion Rate % | Stat card with percentage text and visual progress ring (e.g. '78.4%') | Calculated as (completed enrollments / total enrollments) * 100. | Live metric from /api/forge/stats. | P1 | Completed
92 | Forge Dashboard Overview | Top KPI Metric Cards | Stat Card: Pending / Overdue Assignments | Stat card with Clock/Alert icon showing count of in-progress and overdue assignments | Queries count of enrollments where status IN ('assigned', 'in_progress'). | Live metric from /api/forge/stats. | P1 | Completed
93 | Forge Dashboard Overview | Master Assignments Table | Live Search Input on Assignments Roster | Search bar filtering assignments by employee name, employee code, or course title | Admins can immediately look up any assignment across the company. | Instant client-side filter with debounce. | P1 | Completed
94 | Forge Dashboard Overview | Master Assignments Table | Status Filter Tabs on Assignments | Tabs: 'All Assignments', 'Assigned', 'In Progress', 'Completed', 'Overdue' | Filters the assignments table by lifecycle status. | Allows HR to quickly isolate overdue records for compliance escalation. | P1 | Completed
95 | Forge Dashboard Overview | Master Assignments Table | Department Filter Dropdown on Assignments | Dropdown selecting specific departments to isolate their assignments table | Filters joined employees by department column. | Connects to Employee Central department hierarchy. | P1 | In Progress
96 | Forge Dashboard Overview | Master Assignments Table | Table Action: 'Extend Due Date' | Action button on row: opens date picker modal to grant an extension to an employee | Updates due_date timestamp and logs extension in audit notes. | Prevents unfair overdue marks when employees take medical leave. | P2 | In Progress
97 | Forge Dashboard Overview | Master Assignments Table | Table Action: 'Revoke / Unenroll' | Trash icon button on row: unenrolls employee with confirmation prompt | Deletes enrollment record and associated progress cleanly. | Calls DELETE /api/forge/enrollments/{id}. | P1 | Completed
98 | Forge Dashboard Overview | Learner Self-View | Learner Personalized Dashboard Banner | Non-admin employee view: shows 'Welcome back, [Name]!', active course carousel, and quick resume button | Provides consumer-grade personalized learning homepage for regular employees. | Greets user by first name from Employee Central. | P1 | Completed
99 | Assessment & Quiz Hub | Course Builder Quiz Link | Attach Assessment to Course Module | Button in Course Builder: '+ Attach Final Assessment' | Allows instructor to attach a quiz from Verify Assessment Hub as a mandatory course final exam. | Directly integrates Forge courses with Verify assessment database. | P1 | In Progress
100 | Assessment & Quiz Hub | Course Builder Quiz Link | Configurable Passing Score % Input | Numeric input: 'Minimum Passing Score %' (default 80%) | Course will not mark as completed until the learner achieves this minimum threshold. | Enforces compliance rigor for certification. | P1 | In Progress
101 | Assessment & Quiz Hub | Course Builder Quiz Link | Maximum Allowed Retake Attempts Dropdown | Dropdown: '1 Attempt', '2 Attempts', '3 Attempts', 'Unlimited Attempts' | Controls how many chances a learner has to pass before supervisor intervention is required. | Stores attempt count in forge_progress table. | P2 | In Progress
102 | Assessment & Quiz Hub | Learner Quiz Interface | Timed Exam Interface with Countdown Timer | Prominent countdown clock header with visual warning when under 2 minutes remain | Tests candidate under strict time constraints; automatically submits when timer reaches 00:00. | Protects exam integrity for technical assessments. | P1 | In Progress
103 | Assessment & Quiz Hub | Learner Quiz Interface | Multiple Choice & Multi-Select Question Cards | Card rendering question prompt, code snippets/images, and styled radio/checkbox options | Learner clicks option; highlights in purple pill container; supports keyboard navigation. | Pulls question bank items from Verify module. | P1 | In Progress
104 | Assessment & Quiz Hub | Learner Quiz Interface | Question Navigation Controls | Buttons: '< Previous', 'Next >', and 'Flag Question for Review' button | Allows learner to review questions before final submission; flagged questions show orange dot on grid. | Improves learner test-taking experience. | P2 | In Progress
105 | Assessment & Quiz Hub | Learner Quiz Interface | Action Button: 'Submit Assessment' | Green primary button: 'Submit Assessment' opening confirmation dialog | Calculates score immediately; displays instant results modal with pass/fail status. | Syncs score to forge_enrollments and updates completion status. | P1 | In Progress
106 | Assessment & Quiz Hub | Quiz Results Modal | Scorecard Modal & Performance Breakdown | Modal with celebratory or retry banner, percentage score, correct/incorrect count, and breakdown by topic | Gives immediate diagnostic feedback on learner strengths and weak areas. | Displays 'Retake Quiz' button if attempts remain, or 'Download Certificate' if passed. | P1 | In Progress
107 | Certificates & Verification | Certificate Viewer | Automated PDF Certificate Generator | Server-side PDF generation rendering learner name, course title, completion date, and corporate seals | Generates print-ready high-resolution certificate instantly upon course completion. | Pulls formal employee name from Employee Central. | P1 | In Progress
108 | Certificates & Verification | Certificate Viewer | Interactive Certificate Modal Viewer | Modal previewing certificate with 'Download PDF' and 'Print' action buttons | Learner can preview, save, or print their certificate directly from the browser. | Accessible from My Learning page or Employee Profile tab. | P1 | In Progress
109 | Certificates & Verification | Anti-Fraud | Tamper-Proof Serial Number & QR Code | Embedded unique alphanumeric Certificate ID + scannable QR code on certificate border | Scanning the QR code routes to public verification URL confirming credential authenticity. | Guarantees credibility for external compliance auditors and clients. | P1 | In Progress
110 | Certificates & Verification | Public Verification Page | Public Certificate Verification URL (/verify-certificate/:id) | Standalone public web page displaying green checkmark, recipient name, course name, and issue date | Third parties (auditors, clients, recruiters) can verify certificates without needing an LMS account. | Protects corporate credential integrity. | P1 | In Progress
111 | Certificates & Verification | Social Sharing | Button: 'Add to LinkedIn Profile' | Official LinkedIn credential button: pre-fills course name, issuing organization, and verification URL | Allows employees to celebrate achievements and promotes company employer brand publicly. | Deep link to LinkedIn Add Certification API. | P2 | Planned
112 | Reports & Export Center | Report Configuration | Report Type Selector Dropdown | Dropdown: 'Course Completion Report', 'Department Compliance Audit', 'Overdue Learners Roster', 'Skill Matrix' | Selects which analytical dataset to generate and display in the reporting preview grid. | Pre-formatted for corporate compliance and HR audit submissions. | P1 | In Progress
113 | Reports & Export Center | Report Configuration | Date Range Preset & Custom Picker | Presets: 'Last 7 Days', 'Last 30 Days', 'This Quarter', 'This Year', 'Custom Date Range' | Filters training completion timestamps to match specific audit or review periods. | Essential for quarterly compliance audit filings. | P1 | In Progress
114 | Reports & Export Center | Report Configuration | Department & Designation Multi-Filters | Multi-select dropdowns filtering the report to specific business units or role tiers | Allows HR to generate isolated compliance reports per department (e.g. 'Sales Compliance 2026'). | Directly queries Employee Central master structure. | P1 | In Progress
115 | Reports & Export Center | Export Action Buttons | Export Buttons: 'Export Excel (.xlsx)' & 'Export CSV' | Buttons with Excel and CSV icons: downloads filtered dataset immediately as styled spreadsheet | Generates clean file with employee code, name, department, course, score, and completion timestamp. | Instant one-click audit submission for statutory regulatory reviews. | P1 | In Progress

## Summary
LEARNING CENTRAL (FORGE) — PAGE & MODULE SUMMARY
Roll-up metrics calculated dynamically from the Features sheet. Updates automatically when Priority or Status changes.
Page / Module | Total Features | P1 (Must-Have) | P2 (High-Value) | P3 (Enhancement) | Completed | % Completed
Course Catalogue | 18 | 12 | 6 | 0 | 13 | 72.22%
My Learning Portal | 12 | 10 | 2 | 0 | 11 | 91.67%
Course Player | 12 | 10 | 2 | 0 | 8 | 66.67%
Course Management Studio | 17 | 16 | 1 | 0 | 16 | 94.12%
Assign Training Modal | 11 | 11 | 0 | 0 | 6 | 54.55%
Employee Central Integration | 10 | 5 | 5 | 0 | 0 | 0%
Manager Team Dashboard | 7 | 5 | 2 | 0 | 0 | 0%
Forge Dashboard Overview | 11 | 10 | 1 | 0 | 9 | 81.82%
Assessment & Quiz Hub | 8 | 6 | 2 | 0 | 0 | 0%
Certificates & Verification | 5 | 4 | 1 | 0 | 0 | 0%
Reports & Export Center | 4 | 4 | 0 | 0 | 0 | 0%
TOTAL ALL MODULES | 115 | 93 | 22 | 0 | 63 | 54.78%

## Employee Central Integration
EMPLOYEE CENTRAL (HRMS) & LEARNING CENTRAL INTEGRATION MAP
Technical data flow and touchpoints connecting Employee Central (Deploy) with Learning Central (Forge).
HRMS Touchpoint / Screen | Employee Central Data Entity | Learning Central (Forge) Action | Business Value & User Flow
Employee Profile (/deploy/employees/:code) | employees table (employee_code, name, department, designation, email, manager_id) | Renders new 'Training & Certifications' tab listing active, completed, and overdue courses with progress % and certificate download links. | HR and managers can inspect an employee's continuous learning history directly alongside attendance and salary records.
New Hire Onboarding Pipeline | Employee creation event (POST /api/employees) | Automated rule assigns mandatory compliance curriculum (POSH, InfoSec, Workplace Safety) with 14-day due date. | Zero-touch onboarding: new hires log in on Day 1 to find their mandatory onboarding training ready.
Manager Team View (/deploy/team) | reporting_manager_id relationship in employees table | Filters direct reports and renders team compliance cards, overdue alerts, and one-click 'Nudge' reminder buttons. | Empowers team leads and managers to enforce 100% compliance without having to ask HR for manual spreadsheets.
Department & Role Catalog Filtering | departments and designations master tables in Employee Central | Populates dropdown filters in Course Catalogue and Assign Training modal directly from live HRMS organizational structure. | Ensures course assignments always target active departments and real job roles without duplicate data entry.
Skills Matrix & Competency Profile | employee_skills table (employee_code, skill_id, proficiency_level, verified_badge) | When an employee completes a course with passing score, linked skill tags automatically update to verified status in employee profile. | Eliminates manual skill updating and provides real-time talent capability data for project staffing.
Annual Performance Review (Appraisals) | performance_reviews table in Deploy module | Embeds total training hours, courses completed, and average assessment scores during the appraisal cycle. | Allows managers to quantitatively factor employee learning dedication and upskilling into annual merit raises.
Employee Resignation & Exit Clearance | employee_exit_clearance table in Deploy module | Adds mandatory checklist item verifying all statutory compliance courses were completed prior to generating relieving letter. | Guarantees corporate legal defensibility in case of future regulatory or labor disputes.
Employee Document Vault | employee_documents table in Deploy module | Automatically archives a copy of every earned certificate PDF directly into the employee's HR document repository. | Centralizes all employee credentials in one compliant, searchable archive.